Reporting Period: 04-24-2026 to 5-07-2026

Health System Collaborator: Drs. Craig Glazer & Sara Hennessy 
CIC Operational Lead: Dr. Mujeeb Basit
Project Manager: Aamirah Vadsariya
Project Lead: Kelsea Marble & Mohamed Ali

Overall Status: 🟢 On Track

Executive Summary: Refine clinical detection logic and assess alignment between clinical criteria and billing classifications (POA vs. NPOA). Early findings show notable discrepancies, including shifts in classification when applying vitals- and lab-based logic and potential under- or over-coding.

Recent Achievements:

Completed V3 preprocessing and data transformation:

- Outlier Detection: Implemented physiological-bound checks for vital signs and laboratory values.

- Same-Instant Conflict Resolution: Implemented deterministic resolution of conflicting numerical vital and laboratory measurements occurring at the same instant within an encounter.

- Unified SQL-Based Transformation: Standardized temporal transformation logic using a SQL engine to support consistent Sepsis 1, Sepsis 2, Sepsis 3, POA, and NPOA categorization.

Next steps:

- Duration-Based False-Positive Reduction: Evaluate and implement clinically approved minimum-duration rules for SIRS ≥2 and hypotension periods to reduce false-positive classifications.

- Clinical Logic Updates: Implement the updated septic shock and pulmonary dysfunction criteria.

- Billing Comparison: Compare V3-calculated classifications with billed sepsis classifications and investigate disagreements.

- Results Presentation: Prepare a PowerPoint summarizing the methodology, validation results, billing comparison, and key findings.