Reporting Period: 04-24-2026 to 5-07-2026

Health System Collaborator: Drs. Craig Glazer & Sara Hennessy 
CIC Operational Lead: Dr. Mujeeb Basit
Project Manager: Aamirah Vadsariya
Project Lead: Kelsea Marble & Mohamed Ali

Overall Status: 🟢 On Track

Executive Summary: Refine clinical detection logic and assess alignment between clinical criteria and billing classifications (POA vs. NPOA). Early findings show notable discrepancies, including shifts in classification when applying vitals- and lab-based logic and potential under- or over-coding.

Recent Achievements:

- Refined the pulmonary dysfunction detection logic (see clinical_definitions 3.docx for full specification).

- Established a time-bounded definition of sepsis: once detected, a sepsis episode is monitored over a 14-day window, during which the state persists independently of any change in the underlying infection condition.

- Completed a code review iteration, including resolution of identified bugs.

Next steps:

- Implement the updated pulmonary dysfunction logic.

- Implement sepsis state tracking to monitor episode progression across the encounter.

- Execute the analysis and benchmark the updated algorithm against the previous iteration.

Decision Support Needed:

- Review the Pulmonary dysfunction updated logic in clinical_definitions 3.docx

- Review the note on lab tests/vitals validity