Reporting Period: 02-13-2026 to 2-26-2026

Health System Collaborator: Drs. Craig Glazer & Sara Hennessy 
CIC Operational Lead: Dr. Mujeeb Basit
Project Manager: Aamirah Vadsariya
Project Lead: Kelsea Marble & Mohamed Ali

Overall Status: 🟢 On Track

Executive Summary: Refine clinical detection logic and assess alignment between clinical criteria and billing classifications (POA vs. NPOA). Early findings show notable discrepancies, including shifts in classification when applying vitals- and lab-based logic and potential under- or over-coding.

Recent Achievements:

- Finalized and implemented the updated suspected infection identification logic

- Built the full sepsis severity calculation engine, including SIRS scoring, organ dysfunction detection across six organ systems, and septic shock identification — incorporating patient baseline lab values where applicable

- Refactored the codebase from Jupyter notebooks to modular Python scripts to improve maintainability, reproducibility, and code review workflows

Next steps:

For encounters where sepsis was billed as Not Present on Admission, we will split the population into two groups based on when the calculated sepsis criteria were first met relative to the patient's arrival and evaluate each group across the same set of metrics.

Group 1: NPOA Classification Supported (sepsis criteria first met > 48 hours after arrival): These are cases where the algorithm confirms the NPOA designation, the patient developed sepsis after the 48-hour window.

Group 2: NPOA Classification Potentially Incorrect (sepsis criteria first met ≤ 48 hours after arrival): These are cases where the algorithm suggests sepsis may have been present on admission, raising a potential billing or documentation concern.

For each group, we will analyze:

- How long after arrival sepsis criteria were first met (distribution)

- Which sepsis criteria were already met at the time of the first inpatient order

- Which sepsis criteria were met at the time sepsis was first identified

- Where the patient was admitted from (admission source)

- The highest sepsis severity level that was billed

- The highest sepsis severity level calculated by the algorithm

Decision Support Needed:

- Guidance on defining prophylactic antibiotics or exclusion window after surgical case end

- Validation of the clinical definitions used to identify suspected infection, SIRS criteria, organ dysfunction (across six organ systems), and septic shock — a reference table has been prepared for review.

- Input on the planned validation analysis for NPOA-billed encounters — including any additional metrics or subgroups clinical leadership would like to see.